CICV Best Practice Guide – Practice Note 6: Extension of Time Claims

Introduction

This Practice Note deals with the entitlement of contractors to submit an extension of time and loss and expense claim in accordance with the provisions of the 2024 Standard Building Contract with Quantities. The purpose of these provisions is to allow the contractor to obtain an extension to the Contract Completion Date.

If you are tendering for a Contract that is based on Bespoke Conditions of Contract then you should carefully review the extension of time and loss and expense provisions, as there may be particular requirements that are different from those set out in the Standard Forms

1. Understanding

It is very important, that you understand the provisions of Clause 2.26 Adjustment of Completion Date as this clause sets out your requirements and what you must do to satisfy these contractual provisions. A critical feature is that you follow the notice provisions, and we refer you to our Practice Notes 1 and 1A, which highlight for you requirements for the submission of notices. A further point here is that the submission of notices under this clause is what is known as a condition precedent, and this has recently been established in the Courts as a fundamental obligation to give a notice before in any entitlement can arise.

2. Submitting

A notice is required when it becomes reasonably apparent that the progress of the works or any section is being or is likely to be delayed and your notice has to be sent to the Architect / Contract Administrator.  You are required to provide information on the material circumstances including the cause or causes of the delay, which you have to identify as a Relevant Event.

15 Relevant Events are  identified at Clause 2.29, and you should refer to one or a number of these, depending on the issues that have resulted in a delay.

Clause 2.28 then requires the Architect / Contract Administrator to consider your notice to fix an extension of time, if justified, to the Completion Date and the Architect / Contract administrator has a 12-week period in which to make that judgement.

3. Follow-Up

Clause 2.27.3 then requires you to keep the Architect / Contract Administrator updated on the impact of any delay on the Completion Date, and this may be an ongoing process during the Contract. You can do this by sending communications that record any actual or potential delays, and you should refer to the Relevant Event [s],  and, if possible assess the extent of any further delays on the Completion Date.

4. Managing

The submission of valid notices is critical and you are referred to Practice Notes 1 and 1A on Notices. Equally important is that you keep accurate records of the causes and impact of delays, and you are again referred to Practice Note 2 on Records.

You should be aware of Clause 2.28.5 – which deals with extensions of time after Practical Completion, where the onus is on the Architect / Contract Administrator to review extension of time applications within a 12-week period.

Clause 2.28.6.1 requires that the Contractor must constantly use its best endeavours to prevent delay in the progress of the Works.

Final Advice

- Be proactive in managing the submission of notices.

- Maintain records throughout the project.

- Your extension of time application may be rejected if you have not fully substantiated your position.

- Continually update your submissions.

By implementing these best practices, contractors and subcontractors can ensure clarity, fair compensation and effective commercial management while minimising disputes.

Joint Authors:

Len Bunton – len@buntonconsulting.co.uk
Sean Bradley – sean@seanbradleyconsultancy.co.uk
Mark Holden-Smith – mark@holden-smith.com